AVEPRO

Quality Evaluation and Promotion

PROCEDURES AND THEIR RELATED TIMING

for the External Quality Assessment Process

| WHO | WHAT | WHEN |
| --- | --- | --- |
|  | Establishing the institutional structures (if not yet instituted): (a permanent) Quality Office, Quality Commission, Redaction Committee for the SAR/EEV | 18 months before the site visit |
| HE ISTITUTION | Beginning of the SELF-EVALUATION and SWOT ANALYSIS processes | 12 months before the site visit |
|  | Conclusion of the SELF-EVALUATION Elaboration and DRAFTING of the SER Delivery of the SER to AVEPRO | 6 months before the site visit 3 months before the site visit |
| AVEPRO | Nomination of the Commission of the External Evaluation (EEC) | within 2 months prior to the site visit |
| ISTITUTION and EXTERNAL EVALUATION COMMISSION (EEC) | Definition of the date of the visit (contacts between the Institution and the members of the Evaluation Commission) | within 7 weeks prior to the site visit |
| AVEPRO | Submission of the SER to the External Evaluation Commission | within 6 weeks prior to the site visit Maximum time limit: 4 weeks |
| EE COMMISSION | Analysis of the SER With the help of the Analysis Tool #2: Exchanges on questions and topics to be addressed during the site visit (among the EEC members) | starting 6 weeks before the site visit Distribution of the preparatory self-training and study work of the EEC to be realised in (at least) 4 weeks (a Scheme) |
| ISTITUTION | Travel arrangements for the Evaluation Commission members and related logistics | 5 weeks before the site visit |
| ISTITUTION and EE COMMISSION | Defining of the detailed EE Visit Program |  |
| EE COMMISSION | On-site (or Hybrid) EXTERNAL EVALUATION VISIT by the Evaluation Commission |  |
|  | Drafting of the External Evaluation Report (EER) by the Commission | within 6 weeks after the end of the visit |
|  | Submission of the final draft of the Evaluation Report to the Institution by the President of the External Evaluation Commission. |  |
| ISTITUTION | Possible formal/material corrections or “responses” to the Evaluation Report by the Institution, submitted to the President of the Evaluation Commission (within 2 weeks after the reception of the draft of the Report) → Possibility of an appeal to the contents of the Evaluation Report in case of objections considered substantial by the Institution (see the point 4.4 of the Document A (Guidelines). | within 8 weeks after the end of the visit (within 2 weeks after receiving the final draft of the Report) → In case of an appeal of the HEI, the timeline would be accordingly adjusted. |
| EE COMMISSION | Submission of the External Evaluation Report (final version) by the EEC President to AVEPRO | within 8 weeks after the end of the visit |
| AVEPRO | Sending the External Evaluation Report to the Authorities: Dicastery for Culture and Education, Grand Chancellor, Proper Academic Authorities (Dean, President, Director, Rector); Publication of the Evaluation Report on the Agency’s website (www.avepro.va). | within 10 weeks after the end of the visit |
| ISTITUTION | QUALITY IMPROVEMENT PLAN (QIP) Drafting of the Quality Improvement Plan for the Institution | within 6 months after the site visit |
|  | STRATEGIC PLAN (SP) Drafting and approval of the (quinquennial) Strategic Plan for the Institution | within 12 months after the site visit |
|  | Confirmation or new appointment of Quality Commission and Quality Office members | at least 18 months before a new cycle of the external evaluation visiting procedures. |